## Sheet1
PRIORITY 1: UNDERSTANDING THE RISKS OF DISASTERS AND REINFORCING THE MANAGEMENT
No. | Activity | Key items (sub-activities) | Leading institutions | Bodies participating in the realization of the activity | Planned date for commencement of the activity (quarterly) | Planned date for completion of the activity (quarterly) | Estimated budget | Funding | Success indicator
1 | Assessment of the endangerment of the security for NRM from all risks and hazards | Legally organized and coordinated process including all competent entities (multi-sector approach) | CMC | All entities in SUK verified by the competent governmental bodies that coordinate and manage the crisis management system (Steering committee – SC and Assessment Group – AG) and is adopted by the GRNM | Second quarter of the year | Continuously annually | Budget of CMC | Budget of CMC | Process of updating regularly and extraordinary when needed (Updated assessment)
2 | Assessment of endangerment in the areas of the municipalities and the city of Skopje from all risks and hazards | Legally organized and coordinated process by including all competent bodies (multi-sector approach) on local level | CMC | All entities in SUK on local level (municipalities, ministries, bodies of state administration, other entities) | First quarter of the year | Continuously annually | Budget of CMC | Budget of CMC | Process of updating regularly and extraordinary when needed ( number of updated assessments annually in 80 municipalities and the city of Skopje)
3 | Update and improvement of established database for resources, monitoring daily events | *maintaining resource base *keeping daily log | CMC |  | continuous activity | continuous activity | Budget of CMC | Budget of RNM | number of registered data in the bases
4 | Project for technical support of World Bank for development of National Strategy for Protection and Rescue (financed by EC) | Ongoing project | DPR | / | Ongoing | Ongoing |  | EU Funds | /
5 | Accommodation of endangered population | Preparation of Communiqué to the GRNM and appropriate decisions for activation of special mechanisms (Budget) | MLSP | CMC, DPR | Immediately upon adoption of the decision by the GRNM | after the situation is settled |  | Budget of the GRNM according to the Decision of GRNM
6 | Safety in procurement of oil derivatives | Action Plan for establishing mandatory reserves 2021-2022 | AMOR | AMOR, MF, ME | continuous | continuous | 5,690,788.00 MKD (the amount refers to assets required for establishing the mandatory reserves in amounts defined by law and EU directives, as well as assets required for payment of costs for storage, renewal and control of reserves | AMOR from the account for self-financing activities | Establishing mandatory reserves in amounts that correspond to 90 days of the daily net imports
7 | Security in supplying with oil derivatives | Intervention plan in case of extraordinary disruption in the supply with crude oil and/or oil derivatives | ME | MF, AMOR, ERC | Immediately upon adoption of the decision of the GRNM in pursuance with Article 37 paragraph 5 of the Law on mandatory oil reserves | Immediately upon adoption of the decision of the GRNM in pursuance with Article 37 paragraph 5 of the Law on mandatory oil reserves | It cannot be defined in this phase and will depend on the duration of the oil crisis and the amounts of mandatory reserves that are to be put on the domestic market | Budget of AMOR from the account of the self-financing activities | Efficient response in case of occurrence of an oil crisis and overcoming of the crisis by putting oil derivatives from the mandatory reserves on the market
8 | CRISIS - Overall assessment of risk of the basic services and the transport infrastructure | 1. Assessment of multi-hazards 2. Assessment of the needs and capacity of the institutions in the domain of tackling crises 3. Risk assessment 4. Development of a platform for tackling risks and urgent conditions | University of Ss. Cyril and Methodius, IZIIS | CMC 2. Aristotle University in Thessaloniki Greece 3. Polytechnic University in Tirana, Faculty of Civil Engineering, Albania 4. European Centre for training and research in earthquake engineering, Pavia, Italy | 4/2020 | 4/2022 | 415,392.29 EUR (total budget of the project) 182,105.00 EUR , allocated for the partners from the RNM) | Mechanism for civil protection of EU | Increased capacity of the relevant institutions for cross-border cooperation in the domain for disaster management
9 | L2BR - Learn to be resilient | 1. Pilot studies for protection, readiness and preparedness in conditions of earthquake 2. Feasibility study for implementation of new technologies and innovative approaches in prevention, readiness and preparedness during earthquakes 3. Rulebooks for prevention, readiness and response in case of combined hazard of earthquakes and pandemics | Network of associations of local governments of South-East Europe, France | 1. University Ss. Cyril and Methodius, IZIIS, 2. MoI, Montenegro 3. Municipality of Tirana, Albania 4. IPH Podgorica, Montenegro 5. University of Zagreb, Faculty of Civil Engineering, Croatia | 1/2021 | 2/2022 | 195,431.50 EUR (total budget of the project) 35,333.00 EUR, allocated for IZIIS | EU Civil Protection Mechanism | Improvement of prevention, readiness and response in case of combined hazard from earthquake and pandemics
10 | Instruction materials for control of project documents prepared using Eurocodes – new European regulations for design of structures (EC 0, EC 1, EC 2, EC 3, EC 4, EC 5, EC 6, EC 7, EC 8 и EC 9) | 1. Main aspects of Euro codes 2. Referral to national annexes and nationally defined parameters 3. Resolved practical examples 4. Software solutions and programs available at the market 5. Preparation of final results | University of Ss. Cyril and Methodius, IZIIS | - | 3/2020 | 3/2023 | 10.000,00 EUR (own funds of IZIIS) | University of Ss. Cyril and Methodius, IZIIS | Instruction materials for new European regulations that are part of the national legislation that will be used for training of designers and engineers
11 | Development and upgrade of the network for registration of strong earthquakes Phase 1 – modern database, website and unified approach for data processing | 1. Modern website that contains all necessary information for the stations and the instruments 2. Monitoring the work of the instruments in real time 3. Modern base of quality and safe data whose dissemination can contribute to research in area of engineering seismology and earthquake engineering throughout the world 4. Better approach and increased use of data | University of Ss. Cyril and Methodius, IZIIS | - | 4/2020 | 4/2022 | 10.000,00 EUR (own funds of IZIIS) | University of Ss. Cyril and Methodius, IZIIS | Upgrade and improvement of the functioning of the network for registration of strong earthquakes
12 | Defining the protocol for evaluation of the seismic resilience of existing structures in building construction – seismic certificate т | 1. Evaluation procedure of seismic resilience of existing structures through fast initial review and evaluation system. 2. Procedure for simplified numeric analysis due to evaluation of the seismic resilience of structures. 3. Procedure for final in-depth numeric analysis due to evaluation of the seismic resilience of structures that did not receive a passing grade with the previous two evaluations. | University of Ss. Cyril and Methodius, IZIIS | - | 4/2020 | 4/2022 | 6,000.00 EUR (own funds of IZIIS) | University of Ss. Cyril and Methodius, IZIIS | Product/service applicable on national level for mass registration of the structures when defining the exposure of the construction fund and precise definition of the seismic risk and the condition of the structures for which future interventions are planned
13 | Upgrade of the information system for transport infrastructure and assessment of the seismic risk of new infrastructural objects | 1. Upgrade of information system (IS) with data for new structures: bridges, tunnels and supporting walls with integrated information that refers to vulnerability of every structure. 2. Implementation of the hazardous conditions of each structure. 3. Assessment of risk that includes time component – multiple risk assessment. | University of Ss. Cyril and Methodius, IZIIS | - | 4/2020 | 4/2022 | 6,000.00 EUR (own funds of IZIIS) | University of Ss. Cyril and Methodius, IZIIS | Collecting data and preparation of model of exposure through upgrade of information system for fast and standard assessment of damages and losses upon strong earthquakes
14 | Upgrade and modernization of the existing IZIIS methodology for assessment of damages of earthquake actions | 1. Upgrade and modernization of existing methodology for assessment of damages from earthquake actions 2. Algorithms for statistical processing of data and format of results 3. Supply and analysis of available data for quality upgrade 4. Algorithm for tool integration | University of Ss. Cyril and Methodius, IZIIS | - | 4/2020 | 4/2022 | 6,000.00 EUR (own funds of IZIIS) | University of Ss. Cyril and Methodius, IZIIS | Upgrade and modernization of existing methodology for assessment of damages from earthquake actions
15 | IZIIS - in situ geo laboratory | 1. Creating data base for overall field and laboratory 2. Correlation of field research with laboratory research 3. Instrumentation in soil layers for earthquake registration | University of Ss. Cyril and Methodius, IZIIS | - | 4/2020 | 4/2022 | 6,000.00 EUR (own funds of IZIIS) | University of Ss. Cyril and Methodius, IZIIS | Creating in-situ laboratory with instruments that will enable detailed research of geo-hazards (amplification, interaction ground-structure)
16 | Monitoring of the behaviour of structures in real time with assessment of the level of damage | 1. Use of MSK of real structures through continuous monitoring of their behaviour and 2. Promotion of MSK in the public as an engineering discipline. 3. The data received from this activity can be used for improvement of the existing methods for numeric analyses and design of constructions that are used in IZIIS. 4. Developing directions for monitoring of the condition of various types of structures. 5. Developing an algorithm for assessment of the security of the standing of the structure in real time in conditions of exploitation, upon disasters and extreme events | University of Ss. Cyril and Methodius, IZIIS | - | 4/2020 | 4/2022 | 6,000.00 EUR (own funds of IZIIS) | University of Ss. Cyril and Methodius, IZIIS | Raising the awareness of the need of monitoring the condition of public capital structures. Expanding and deepening of the current activities of IZIIS, as well as monitoring the world trends.
17 | Development and upgrade of the Network for registration of strong earthquakes Phase 1 – modern database, website and unified approach for data processing | 1. Modern website that contains all necessary information for stations and instruments 2. Monitoring the work of the instruments in real time 3. Modern base of quality and secure data whose dissemination can contribute to research in the area of engineering seismology and earthquake engineering throughout the world 4. Better approach and increased use of data | University of Ss. Cyril and Methodius, IZIIS | - | 4/2020 | 4/2022 | 6,000.00 EUR (own funds of IZIIS) | University of Ss. Cyril and Methodius, IZIIS | Надградба и унапредување на функционирањето на мрежата за регистрација на силни земјотреси
18 | Defining a Protocol for evaluation of seismic resilience of existing structures in building construction - seismic certificate | 1. Procedure for evaluation of seismic resilience of existing structures through fast initial review and evaluation system. 2. Procedure for simplified numerical analysis due to evaluation of seismic resilience of structures 3. Procedure for final in-depth numerical analysis due to evaluation of the seismic resilience of structures that were not well-assessed in the two previous evaluations. | University of Ss. Cyril and Methodius, IZIIS | - | 4/2020 | 4/2022 | 6,000.00 EUR (own funds of IZIIS) | University of Ss. Cyril and Methodius, IZIIS | Product/service applicable on national level for mass registration of structures when defining the exposure of the construction fund and precise definition of the seismic risk and the condition of the structures for which future interventions are planned
19 | Upgrade of the information system for transport infrastructure and assessment of seismic risk of new infrastructural structures | 1. Upgrade of information system with data for new structures: bridges, tunnels and supporting walls with integrated information that refers to the vulnerability of each structure. 2. Implementation of hazard conditions of each structure. 3. Risk assessment that includes time component - multifold risk assessment. | University of Ss. Cyril and Methodius, IZIIS | - | 4/2020 | 4/2022 | 6,000.00 EUR (own funds of IZIIS) | University of Ss. Cyril and Methodius, IZIIS | Collecting data for preparation of exposure model through upgrade of the information system for fast and standard assessment of damages and losses after strong earthquakes
20 | Eq-DAT: Upgrade and modernization of the existing IZIIS methodology for assessment of damages from earthquake actions | 1. Upgrade and modernization of existing methodology for assessment of damages from earthquake actions 2. Algorithm for statistical data processing and form of results 3. Securing and analysis of available data for quality upgrade 4. Algorithm for tool integration | University of Ss. Cyril and Methodius, IZIIS | - | 4/2020 | 4/2022 | 6,000.00 EUR (own funds of IZIIS) | University of Ss. Cyril and Methodius, IZIIS | Upgrade and modernization of the existing methodology for damage assessment from earthquake actions
21 | IZIIS in-situ geo laboratory | 1. Creating data base with overall field and laboratory 2. Co-relation of field research with laboratory research 3. Instrumentation in soil layers for earthquake registration | University of Ss. Cyril and Methodius, IZIIS | - | 4/2020 | 4/2022 | 6,000.00 EUR (own funds of IZIIS) | University of Ss. Cyril and Methodius, IZIIS | Creating in-situ laboratory that is instrumentized and will enable detailed research for geo-hazards (amplification, interaction field-structure)
22 | Monitoring of the behaviour of structures in real-time assessing the damage level | 1. Using MCF for real structures using continuous follow up of their behaviour and 2. Promotion of MCF in the public as an engineering discipline 3. The data resulting from this activity will be used for enhancement of the existing methods for numeric analysis and design of constructions that will be used in IZIIS 4. Developing directions for monitoring the condition of various types of structures 5. Developing algorithm for assessment of security of the condition of the structure in real-time in conditions of exploitation after disaster and extreme events. | University of Ss. Cyril and Methodius, IZIIS | - | 4/2020 | 4/2022 | 6,000.00 EUR (own funds of IZIIS) | University of Ss. Cyril and Methodius, IZIIS | Raising the public awareness for the need of monitoring the condition of public capital structures. Expanding and deepening of the activities so far undertaken by IZIIS, as well as monitoring the world trends.
23 | Development and upgrade of the Network for registration of strong earthquakes, Phase - 1 modern data base, website and unified approach for data processing | 1. Modern website that contains all necessary information for pages and instruments 2. Monitoring the work of the instruments in real time 3. Modern base of quality and reliable information whose dissemination can contribute to research in the area of engineering seismology and earthquake engineering throughout the world 4. Better access and increased use of data | University of Ss. Cyril and Methodius, IZIIS | - | 4/2020 | 4/2022 | 6,000.00 EUR (own funds of IZIIS) | University of Ss. Cyril and Methodius, IZIIS | Upgrade and enhancement of the functioning of the network for registration of strong earthquakes
24 | Defining the protocol for evaluation of the seismic resilience of existing structures in building construction - seismic certificate | 1. Procedure for evaluation of seismic resilience of existing structures through fast initial review and evaluation system 2. Procedure for simplified numerical analysis due to evaluation of seismic resilience of structures 3. Procedure for final in-depth numerical analysis due to evaluation of seismic resilience of structures which did not pass the previous two evaluations | University of Ss. Cyril and Methodius, IZIIS | - | 4/2020 | 4/2022 | 6,000.00 EUR (own funds of IZIIS) | University of Ss. Cyril and Methodius, IZIIS | Product/service applicable on national level for mass registration of structures when defining the exposure of the construction fund and precise definition of the seismic risk and condition of the structures for which future interventions are planned
25 | Upgrade and modernization of the information system for transport infrastructure and assessment of the seismic risk of new infrastructural structures | 1. Upgrade of information system (IS) with data for new structures: bridges, tunnels and supporting walls with integrated information referring to the vulnerability of each structure 2. Implementation of the hazardous conditions on each structure 3. Risk assessment including time component – multifold risk assessment | University of Ss. Cyril and Methodius, IZIIS | - | 4/2020 | 4/2022 | 6,000.00 EUR (own funds of IZIIS) | University of Ss. Cyril and Methodius, IZIIS | Collecting data and preparation of an exposure model by upgrading the information system for fast and standard damage assessment and losses after strong earthquakes
26 | Upgrade and modernization of the existing IZIIS methodology for damage assessment of earthquake actions | 1. Upgrade and modernization of the existing methodology for damage assessment from earthquake actions 2. Algorithms for statistical data processing and form of results 3. Securing and analysis of available data for qualitative upgrade 4. Algorithm for tool integration | University of Ss. Cyril and Methodius, IZIIS | - | 4/2020 | 4/2022 | 6,000.00 EUR (own funds of IZIIS) | University of Ss. Cyril and Methodius, IZIIS | Upgrade and modernization of the existing methodology for damage assessment of earthquake actions
27 | IZIIS in-situ geo laboratory | 1. Creating data base for overall field and laboratory research 2. Co-relation of field research with laboratory research 3. Instrumentation in soil layers for earthquake registration | University of Ss. Cyril and Methodius, IZIIS | - | 4/2020 | 4/2022 | 6,000.00 EUR (own funds of IZIIS) | University of Ss. Cyril and Methodius, IZIIS | Creating In-situ laboratory, with instruments, that will enable detailed research of geo-hazards (amplification, interaction field-structure)
28 | Monitoring the behaviour of structures in real time by assessing the level of damage | 1. Use of MCF on real structures using continuous monitoring of their behaviour 2. Promotion of MCF in the public as an engineering discipline 3. Data received from this activity will be used for improvement of the existing method for numerical analysis and design of structures which are used in IZIIS 4. Developing directions for monitoring of the condition of various types of structures 5. Developing algorithm for assessment of security of the condition of the structure in real-time in conditions of exploitation after disasters and extreme events | University of Ss. Cyril and Methodius, IZIIS | - | 4/2020 | 4/2022 | 6,000.00 EUR (own funds of IZIIS) | University of Ss. Cyril and Methodius, IZIIS | Raising the public awareness for the need of monitoring the condition of public capital structures Expanding and deepening of the previous activities of IZIIS, as well as monitoring of world trend.
29 | Development and upgrade of the Network for registration of strong earthquakes Phase 1 – modern data base, web site and unified approach to data processing | 1. Modern website that contains all necessary information for stations and instruments 2. Monitoring the work of the instruments in real time 3. Modern base of quality and secure data whose dissemination can contribute to research in the area of engineering seismology and earthquake engineering throughout the world 4. Better approach and increased use of data | University of Ss. Cyril and Methodius, IZIIS | - | 4/2020 | 4/2022 | 6,000.00 EUR (own funds of IZIIS) | University of Ss. Cyril and Methodius, IZIIS | Upgrade and enhancement of the functioning of the network for registration of strong earthquakes
30 | Defining a protocol for evaluation of seismic resilience of existing structures in building construction - seismic certificate | 1. Modern website that contains all necessary information for pages and instruments 2. Monitoring the work of the instruments in real time 3. Modern base for quality and reliable data whose dissemination can contribute to research in area of engineering seismology and earthquake engineering throughout the world 4. Better approach and increased use of data | University of Ss. Cyril and Methodius, IZIIS | - | 4/2020 | 4/2022 | 6,000.00 EUR (own funds of IZIIS) | University of Ss. Cyril and Methodius, IZIIS | Product/service applicable on national level for mass registration of structures when defining the exposure of the construction fund and precise definition of the seismic risk and condition of the structures for which future interventions are planned
31 | Upgrade and modernization of the information system for transport infrastructure and assessment of the seismic risk of new infrastructural structures | 1. Upgrade of information system (IS) with data for new structures: bridges, tunnels and supporting walls with integrated information referring to the vulnerability of each structure 2. Implementation of the hazardous conditions on each structure 3. Risk assessment including time component – multifold risk assessment | University of Ss. Cyril and Methodius, IZIIS | - | 4/2020 | 4/2022 | 6,000.00 EUR (own funds of IZIIS) | University of Ss. Cyril and Methodius, IZIIS | Collecting data and preparation of an exposure model by upgrading the information system for fast and standard damage assessment and losses after strong earthquakes
32 | Eq-DAT: Upgrade and modernization of the existing IZIIS methodology for assessment of damages from earthquake actions | 1. Upgrade and modernization of the existing methodology for damage assessment from earthquake actions 2. Algorithms for statistical data processing and form of results 3. Securing and analysis of available data for qualitative upgrade 4. Algorithm for tool integration | University of Ss. Cyril and Methodius, IZIIS | - | 4/2020 | 4/2022 | 6,000.00 EUR (own funds of IZIIS) | University of Ss. Cyril and Methodius, IZIIS | Upgrade and modernization of the existing methodology for damage assessment from earthquake actions
33 | IZIIS in-situ geo laboratory | 1. Creating data base for overall field and laboratory research 2. Co-relation of field research with laboratory research 3. Instrumentation in soil layers for earthquake registration | University of Ss. Cyril and Methodius, IZIIS | - | 4/2020 | 4/2022 | 6,000.00 EUR (own funds of IZIIS) | University of Ss. Cyril and Methodius, IZIIS | Creating In-situ laboratory, with instruments, that will enable detailed research of geo-hazards (amplification, interaction field-structure)
34 | Monitoring the behaviour of structures in real time by assessing the level of damage | 1. Use of MCF on real structures using continuous monitoring of their behaviour 2. Promotion of MCF in the public as an engineering discipline 3. Data received from this activity will be used for improvement of the existing method for numerical analysis and design of structures which are used in IZIIS 4. Developing directions for monitoring of the condition of various types of structures 5. Developing algorithm for assessment of security of the condition of the structure in real-time in conditions of exploitation after disasters and extreme events | University of Ss. Cyril and Methodius, IZIIS | - | 4/2020 | 4/2022 | 6,000.00 EUR (own funds of IZIIS) | University of Ss. Cyril and Methodius, IZIIS | Raising the public awareness for the need of monitoring the condition of public capital structures Expanding and deepening of the previous activities of IZIIS, as well as monitoring of world trend.
35 | Development and upgrade of the Network for registration of strong earthquakes Phase 1 – modern data base, web site and unified approach to data processing | 1. Modern website that contains all necessary information for pages and instruments 2. Monitoring the work of the instruments in real time 3. Modern base for quality and reliable data whose dissemination can contribute to research in area of engineering seismology and earthquake engineering throughout the world 4. Better approach and increased use of data | University of Ss. Cyril and Methodius, IZIIS | - | 4/2020 | 4/2022 | 6,000.00 EUR (own funds of IZIIS) | University of Ss. Cyril and Methodius, IZIIS | Upgrade and enhancement of the functioning of the network for registration of strong earthquakes
36 | Defining the protocol for evaluation of the seismic resilience of existing structures in building construction - seismic certificate | 1. Procedure for evaluation of seismic resilience of existing structures through fast initial review and evaluation system 2. Procedure for simplified numerical analysis due to evaluation of seismic resilience of structures 3. Procedure for final in-depth numerical analysis due to evaluation of seismic resilience of structures which did not pass the previous two evaluations | University of Ss. Cyril and Methodius, IZIIS | - | 4/2020 | 4/2022 | 6,000.00 EUR (own funds of IZIIS) | University of Ss. Cyril and Methodius, IZIIS | Product/service applicable on national level for mass registration of structures when defining the exposure of the construction fund and precise definition of the seismic risk and condition of the structures for which future interventions are planned
37 | Upgrade and modernization of the information system for transport infrastructure and assessment of the seismic risk of new infrastructural structures | 1. Upgrade of information system (IS) with data for new structures: bridges, tunnels and supporting walls with integrated information referring to the vulnerability of each structure 2. Implementation of the hazardous conditions on each structure 3. Risk assessment including time component – multifold risk assessment | University of Ss. Cyril and Methodius, IZIIS | - | 4/2020 | 4/2022 | 6,000.00 EUR (own funds of IZIIS) | University of Ss. Cyril and Methodius, IZIIS | Collecting data and preparation of an exposure model by upgrading the information system for fast and standard damage assessment and losses after strong earthquakes
38 | Eq-DAT: Upgrade and modernization of the existing IZIIS methodology for assessment of damages from earthquake actions | 1. Upgrade and modernization of the existing methodology for damage assessment from earthquake actions 2. Algorithms for statistical data processing and form of results 3. Securing and analysis of available data for qualitative upgrade 4. Algorithm for tool integration | University of Ss. Cyril and Methodius, IZIIS | - | 4/2020 | 4/2022 | 6,000.00 EUR (own funds of IZIIS) | University of Ss. Cyril and Methodius, IZIIS | Upgrade and modernization of the existing methodology for damage assessment from earthquake actions
39 | IZIIS in-situ geo laboratory | 1. Creating data base for overall field and laboratory research 2. Co-relation of field research with laboratory research 3. Instrumentation in soil layers for earthquake registration | University of Ss. Cyril and Methodius, IZIIS | - | 4/2020 | 4/2022 | 6,000.00 EUR (own funds of IZIIS) | University of Ss. Cyril and Methodius, IZIIS | Creating In-situ laboratory, with instruments, that will enable detailed research of geo-hazards (amplification, interaction field-structure)
40 | Monitoring the behaviour of structures in real time by assessing the level of damage | 1. Use of MCF on real structures using continuous monitoring of their behaviour 2. Promotion of MCF in the public as an engineering discipline 3. Data received from this activity will be used for improvement of the existing method for numerical analysis and design of structures which are used in IZIIS 4. Developing directions for monitoring of the condition of various types of structures 5. Developing algorithm for assessment of security of the condition of the structure in real-time in conditions of exploitation after disasters and extreme events | University of Ss. Cyril and Methodius, IZIIS | - | 4/2020 | 4/2022 | 6,000.00 EUR (own funds of IZIIS) | University of Ss. Cyril and Methodius, IZIIS | Raising the public awareness for the need of monitoring the condition of public capital structures Expanding and deepening of the previous activities of IZIIS, as well as monitoring of world trends
41 | Development of local strategies for disaster risk reduction | Building capacities of representatives of the municipal administration for preparation, implementation and monitoring of local strategies for disaster risk reduction | ZELS | DPR - expert support | september 2022 |  | 60000 | ZELS Budget | training conducted for representatives of the municipalities
42 | Development of local plans for protection and rescue of various types of risks | Building capacities of representatives of the municipal administration for preparation, implementation and monitoring of local plans for protection and rescue from various types of risks | ZELS | DPR - expert support | november2022 |  | 60000 | ZELS Budget | counselling conducted for the municipalities
43 | Preparation of a strategy for protection and rescue on the territory of the city of Skopje | Increase of capacities for protection and rescue of the city of Skopje for the construction of the gas network | City of Skopje | Sectors of the city of Skopje GA-MA | september 2022 |  | 60000 | Budget of the city of Skopje | Report for the overall gas network, connections etc.
44 | Construction of plan for construction of 2 sub-centres in the city of Skopje | Plan and project for construction of 2 fire-fighting sub-centres in the municipalities Butel and Kisela Voda | City of Skopje | City of Skopje, municipalities Butel and Kisela Voda | january 2022 |  | 3.000.000,00 | Budget of the city of Skopje | Coverage on the territory mapped as risky for fires and increased number of objects
45 | Strategy for protection of fires, floods, earthquakes, on the territory of the city of Skopje | Preparation of a Strategy for mapping and coverage of key items that are critical for occurrence of larger disasters and hazards for the city of Skopje | City of Skopje | City of Skopje | October 2021-May 2022 | 2022-05-01 | / |  | defining critical points and improvement of capacities for protection and rescue
46 | Strategic plan for disaster risk reduction | Defining the weaknesses in the system for protection and rescue | City of Skopje | Civil engineering sector | 2021 | 2024 |  | / | defining of measures and assigning directions for prevention
47 | Preparation of a plan for equipping and filling of FF units in NRM | National Strategy for equipping of FF units in RNM - vehicles, employees and equipment | MLSG |  | 2021 | 2025 | / | Budget of the Government of RNM | Modernization of the equipment and more efficient intervention in risks
48 | Implementation of NIKS program | National Strategy for disaster risk reduction, mapping and defining of the area | CMC | CMC, DPR | 2019 | / | / | / | Mapping of risks and disasters on territories