## Sheet1
PRIORITY 3: IMPROVEMENT OF PREPARATION FOR EFFECTIVE RESPONSE
No. | Activity | Key items (sub-activities) | Leading institutions | Bodies participating in the realization of the activity | Planned date for commencement of the activity (quarterly) | Planned date for completion of the activity (quarterly) | Estimated budget | Funding | Success indicator
1 | Preparation of MoI for prevention, first response and tackling risks and disasters | Preparation and updating operational plans pursuant to the Assessment of hazard of the Republic of North Macedonia from natural and other disasters | MOI | UIP, USPSQC and other units of MoI and NSB | Ongoing | Ongoing process |  | MOI of RNM | High priority
2 | Discovery and sanctioning of perpetrators of crimes related to WMDs, radioactive materials, explosive devices and other crimes | Exchange of information with Europol/Interpol, undertaking tactical and operational measures | MOI | Organization units of MoI and NSB | Ongoing | Ongoing process |  | MOI of RNM | High priority
3 | Undertaking measures and actions for prevention of transmission of COVID 19 | Measures and activities for implementation of the decisions and measures of the GRNM, Law on Protection of the Population from infectious diseases, support to the MH | MOI | Organization units of MoI and NSB | Ongoing | Until pandemic is over, pursuant to the recommendations of WHO |  | MOI of RNM | High priority
4 | Support from the Army to national institutions and local self-government units (in case of state of emergency and crisis situations and natural or other disasters) | Strategic priorities Engaging of certain capacities of the Army for active participation in operations for support of the police, national institutions, local self-government units and other entities and institutions in case of emergency or crisis situation, as well as in support of the institutions in the country when tackling consequences of natural and other disasters, as well as in conditions of diseases in wider extend and epidemics and in conditions of technical and technologic disasters | MoD/Army | Engaging declared forces from the Army for tackling crisis situations (mobile infantry forces, forces for ambulance support, forces for NBC, engineering forces, forces for logistical support, helicopter forces for air support and air transport - medical evacuation, search and rescue ) | 01.01.2022 | 31.12.2022 | 11239150 | Government of the Republic of North Macedonia | In order to fast and efficiently engage the Army when executing tasks in case of emergency or crisis situation and natural and other disasters, mechanisms must be provided that will resolve the additional funding of the Army i.e. to define it with a certain percentage of the budget additional funds for the Army.
5 | Accommodation of endangered population | on field registration of damage | NIIMCSA | NIIMCSA, Red Cross, Local self-government, MTC and CMC | Upon occurrence of natural disaster | Upon ending of the situation | Accommodating 200 persons up to 90 days 18,000,000 MKD | Budget of the RNM/MLSP in pursuance to the Decision of the GRNM | Purposed funds upon conclusions and number of accommodated persons
|  | Preparation of Communiqué to the GRNM and adequate decisions for activation of special mechanisms (budget funds are secured upon a Decision is adopted by the Government) | MLSP | CMC, DPR | Immediately upon a decision is adopted by the GRNM | Upon ending of the situation |  | Budget of the RNM pursuance to the Decision of GRNM
Preparation of a Report for a given period and the Communiqué to the GRNM if there is need of further accommodation until the situation ends / mechanisms (budget funds are secured upon a Decision is adopted by the Government)
6 | Assigning national coordinator for response to the healthcare system in urgent situations, crisis situations and disasters. The work tasks for national coordinator are: - Manages the coordinative body for preparation and response to the healthcare system in tackling urgent situations, crisis situations and disasters; - Convenes meetings of the Coordinative body for preparation and response to the healthcare system in tackling urgent situations, crisis situations and disasters; - Proposes annual action plan for preparation of the healthcare system in tackling urgent situations, crisis situations and disasters; - Follows the implementation of the annual action plan for preparation of the healthcare system when tackling urgent situations, crisis situations and disasters, performs corrections and provides report for the Coordinative body within MH for preparation and response in urgent situations, crisis situations and disasters; - Monitors the continuous check and update of operational plans for preparation and response to the hospitals and other healthcare institutions in tackling urgent situations, crisis situations and disasters; - Cooperates with national and local healthcare and other institutions and organizations in pursuance to the needs; - Communicates and coordinates other bodies and organs in the system for tackling urgent situations, crisis situations and disasters i.e. the GS within the CMC and the GS within DPR, Steering committee in the Government of the Republic of North Macedonia and other relevant bodies; - Communicates and coordinates international organizations and donors engaged in tackling urgent situations, crisis situations and disasters; - Leads preparation of plans, strategies, reports and finds solutions for problems in the interest of preparation and response of the healthcare system in tackling urgent situations, crisis situations and disasters; - Shares reports and other materials to the national and local government in conditions of urgent and crisis situations and disasters; - Cooperates with relevant institutions in collection or assessment of basic demographic data in the struck crisis area; - Follows the activities in the struck crisis area in pursuance to the general operational procedures for response of the healthcare sector in urgent, crisis situations and disasters; - Analyzes the data and proposes effective measures and activities; - Is responsible for initiating actions for following the plan and proposing of measures. Profession and qualifications of the national coordinator: - High education and post-graduate studies in the area of health, health management, public health, health economy, social studies and other similar areas; - Minimum 5 years of professional experience in the healthcare protection in conditions of crisis and emergency situations; - Minimum 5 years of experience in preparation and response of the healthcare system in crisis and emergency situation; - Possesses organizational skills, skills in preparation of reports and data analysis, as well as experience in work with national and local institutions and organizations; - Experience in cooperation with international organizations; - Knowledge and training in the area of preparation and response of the healthcare system in crisis situations; - Substantial knowledge of English language. | Assigning a coordinative body | MH |  | January 2020 | March 2022 | 1,5 million MKD annually for monthly lump sums for participation | Budget of MH | Official functioning of the coordinative body
7 | Assigning national coordinator for response to the healthcare system in urgent situations, crisis situations and disasters. The work tasks for national coordinator are: - Manages the coordinative body for preparation and response to the healthcare system in tackling urgent situations, crisis situations and disasters; - Convenes meetings of the Coordinative body for preparation and response to the healthcare system in tackling urgent situations, crisis situations and disasters; - Proposes annual action plan for preparation of the healthcare system in tackling urgent situations, crisis situations and disasters; - Follows the implementation of the annual action plan for preparation of the healthcare system when tackling urgent situations, crisis situations and disasters, performs corrections and provides report for the Coordinative body within MH for preparation and response in urgent situations, crisis situations and disasters; - Monitors the continuous check and update of operational plans for preparation and response to the hospitals and other healthcare institutions in tackling urgent situations, crisis situations and disasters; - Cooperates with national and local healthcare and other institutions and organizations in pursuance to the needs; - Communicates and coordinates other bodies and organs in the system for tackling urgent situations, crisis situations and disasters i.e. the GS within the CMC and the GS within DPR, Steering committee in the Government of the Republic of North Macedonia and other relevant bodies; - Communicates and coordinates international organizations and donors engaged in tackling urgent situations, crisis situations and disasters; - Leads preparation of plans, strategies, reports and finds solutions for problems in the interest of preparation and response of the healthcare system in tackling urgent situations, crisis situations and disasters; - Shares reports and other materials to the national and local government in conditions of urgent and crisis situations and disasters; - Cooperates with relevant institutions in collection or assessment of basic demographic data in the struck crisis area; - Follows the activities in the struck crisis area in pursuance to the general operational procedures for response of the healthcare sector in urgent, crisis situations and disasters; - Analyzes the data and proposes effective measures and activities; - Is responsible for initiating actions for following the plan and proposing of measures. Profession and qualifications of the national coordinator: - High education and post-graduate studies in the area of health, health management, public health, health economy, social studies and other similar areas; - Minimum 5 years of professional experience in the healthcare protection in conditions of crisis and emergency situations; - Minimum 5 years of experience in preparation and response of the healthcare system in crisis and emergency situation; - Possesses organizational skills, skills in preparation of reports and data analysis, as well as experience in work with national and local institutions and organizations; - Experience in cooperation with international organizations; - Knowledge and training in the area of preparation and response of the healthcare system in crisis situations; - Substantial knowledge of English language. | Assigning a national coordinator | MH |  | January 2020 | March 2022 | 150,000 MKD lump sum annually | Budget of MH | Assigned national coordinator
8 | Monitoring and evaluation of the current situation Audit and update of the plans for preparation for urgent, crisis and emergency situations and disasters on the level of the healthcare institution, mostly: hospitals – including urgent centres, healthcare homes – including the emergency medical aid services. All national and private institutions from the primary, secondary and tertiary healthcare protection. Moreover, the PHI and the PHC, the National Health and Sanitary Inspectorate, MALMED, Food and Veterinary Agency and Agency for Radiation Safety. Preparation and adoption of a plan for regular update of the plans for readiness for urgent, crisis, emergency conditions and disasters on the level of the healthcare institution. Audit of the roles, responsibilities and authorizations of each person included in the plans for readiness in urgent and crisis situations and disasters. Procedures for mobilization of staff and information on roles, responsibilities and authorizations of those involved. Assessment of needs of trainings for: assessment, risk management, trainings for infectious diseases management, preparation of response hospitals – including medical nurses, medical and non-medical staff for response in urgent, crisis situations and disasters. Audit and updating of procedures for coordination and fast supply and distribution of external resources (coordination, request, receipt, storage of medicines, registration, dispersion, control and securing storages) from the Agency of stock reserves – antibiotics, chemical antidotes, antitoxins, essential medicines, intravenous equipment, materials for maintenance of respiratory ways and medical/surgical items. |  | MH | MH, NHI, PHI, PHI, PHC, MALMED, FVA, ARS, NSHI | April 2022 | December 2022 |  | Budget of MH | Prepared/ revised / updated plans for readiness on the level of each institution
9 | Health information Mapping and updating data for: health institutions (public and private), pharmacies and medical stores, freezers, laboratories, blood availability, human resources (medical), medical materials and equipment, accommodating capacities and transport vehicles Mapping of disposable human resources and roles: doctors, medical nurses, paramedics, drivers, administrative staff, laboratory technicians, dispatchers, communication specialists in public and private health institutions. Preparation of a special module of the healthcare information system MOJ TERMIN that will be available for the needs and requests of all stakeholders for response to the urgent and crisis situation and disaster and will offer updated information that will be of key importance for efficient and fast assessment of available resources and their appropriate use. | Mapping and updating relevant data for health infrastructure |  | MH, MOJ TERMIN | April 2022 | December 2022 |  | Budget of MH | Mapped data, sorted information and established special module in MOJ TERMIN that enables fast access to all involved entities
10 | Operational procedures Preparation/audit/update of procedure, directions and protocols for fast assessment of health needs in urgent, crisis situations and disasters Preparation/audit/update of procedure, directions and protocols for communications during urgent, crisis situations – timely and transparent informing, coordination of communication with stakeholders and relevant stakeholders: media and population, inter-sector communication, communication within the healthcare sector Audit/update of general operational procedures for reaction of the healthcare sector in urgent/crisis situations and disasters (Annex 1) Audit/update of general operational procedures for communication of the healthcare sector in urgent, crisis situations and disasters (Annex 2) Audit/update of standard operational procedures for public health response during floods (Annex 3) | Preparation/update/audit of procedures | MH - Coordinative body |  | April 2022 | December 2022 |  | Budget of MH | Prepared/revised/updated and adopted procedures for response in urgent and crisis situations and disasters
11 | Conducting trainings and exercises Conducting trainings and simulation exercises based on previously prepared/updated procedures and plans for response of the coordinative body and the health institutions on the level of a region where all stakeholders are included from the healthcare sector within one region, as well as more affected regions. Simulation exercises are conducted based on one or more of the following types of urgent, crisis situations and disasters: Hydro-meteorological: floods, storms, extreme temperatures, drought, forest fires / fires in open spaces Geo-physical: earthquakes, leakage of chemical substances, demolition of industrial infrastructure, explosions, fires, radiation, traffic accidents in air traffic, maritime traffic, road traffic, railway traffic Economic crisis: deepening of economic collapse, hyperinflation, financial crises and currency crises Violence: terrorism, civil disturbances, civil war, war | Conducting trainings and simulation exercises | MH |  | January 2022 | December 2024 |  | Budget of MH | Conducted trainings of all persons involved and simulation exercises for all adopted plans and procedures / protocols on the level of a health institution
12 | Ongoing maintenance and upgrade of the existing systems for early warning of floods, draughts and other weather disasters | Supply of a new radar |  | AHM | 2022 | 2022 | 100000000 | Budget of RNM
|  | New employments | AHM | AHM | 2022 | 2022 | 5000000 | Budget of RNM
|  | Increase of the compensation for the individuals who perform hydro-meteorological measurements and surveys | AHM | AHM | 2022 | 2022 | 10000000 | Budget of RNM
|  | Current (minimal) maintenance of the existing systems for early warning from floods, draughts and other weather disasters | AHM | AHM | 2022 | 2024 | 1000000 | Budget of RNM
13 | Construction works and preparation of a façade for the Museum Sveti Nikole | Protection of capillary humidity | APCH | Museum Sveti Nikole | 01.10.2021 - 31.12.2021 | 01.07.2024 - 31.09.2024 | 2460000 | Budget of RNM | Complete realization of sub-activity
14 | Spa Bansko v. Bansko Strumica | Video surveillance | APCH | Museum Strumica | 01.10.2021 - 31.12.2021 | 01.07.2024 - 31.09.2024 | 30000 | Budget of RNM | Complete realization of sub-activity
15 | Protection of exhibited materials | Depot shelves, glass cases and showcases | APCH | Museum Negotino | 01.10.2021 - 31.12.2021 | 01.07.2024 - 31.09.2024 | 620000 | Budget of RNM | Complete realization of sub-activity
16 | Reparation of the Museum of National Liberation Struggle Krushevo | Roof reparation, change of doors and windows, video surveillance and devices for humidity treatment | APCH | Museum Krushevo | 01.10.2021 - 31.12.2021 | 01.07.2024 - 31.09.2024 | 3100000 | Budget of RNM | Complete realization of sub-activity
17 | Protection of exhibited museum materials | Construction works, shelves and devices for humidity treatment | APCH | National Institution Museum Veles | 01.10.2021 - 31.12.2021 | 01.07.2024 - 31.09.2024 | 690000 | Budget of RNM | Complete realization of sub-activity
18 | Museum Terakota Vinica | Video surveillance, 3D modelling of archaeological objects | APCH | Museum Vinica | 01.10.2021 - 31.12.2021 | 01.07.2024 - 31.09.2024 | 340000 | Budget of RNM | Complete realization of sub-activity
19 | Museum arrangement | Depot, alarm devices, video surveillance and FF devices | APCH | Museum Nikola Nezlobinski Struga | 01.10.2021 - 31.12.2021 | 01.07.2024 - 31.09.2024 | 750000 | Budget of RNM | Complete realization of sub-activity
20 | Depot arrangement | mechanical protection, equipment for micro-climate conditions, lightning conditions, FF protection | APCH | National Institution Museum Kumanovo | 01.10.2021 - 31.12.2021 | 01.07.2024 - 31.09.2024 | 1300000 | Budget of RNM | Complete realization of sub-activity
21 | Museum arrangement | Video surveillance, humidity measuring devices, shelves and alarm systems | APCH | National Institution and Museum Prilep | 01.10.2021- 31.12.2021 | 01.07.2024-31.09.2024 | 500000 | Budget of RNM | Complete realization of sub-activity
22 | Implementation and introduction of the European number for urgent calls E-112 | Basic process of data processing in the system; Systemic architecture for E-112; Functions of the system that are relevant to the organizations - users; Receiving calls and creating incidents; Incident management; preparation of the subjects that will be using the system and tasks and responsibility of the subject participants and users. The main call centre in Skopje is already completed and in the course of 2020 the renovation of the regional premises will continue with a budget awarded from the Government | CMC | All entities in SUK | Continuous | Continuous |  | EC within the frames of the Action programme for 2016 (IPA 2016/039-618/02.02 / MK / Migration and asylum, border management and fight). GRNM provided funds for renewal, reconstruction, adaptation of the premises for the operational centre Е-112. CMC Budget | Total implementation and functionality of E-112 in all phases
23 | Project Comprehensive RISK assessment of basic services and transport Infrastructure (CRISIS)“ | Cross-border assessment of several hazards; assessment of needs; cross-border management of several risks and development of cross-border web-base platform for assessment and risk management | University of Ss. Cyril and Methodius, IZIIS, CMC | University of Ss. Cyril and Methodius, IZIIS, CMC with three institutions from Italy, Greece and Albania | 2020 | 2022 | 42,000 EUR |  | Improved cross border cooperation and coordination in risk management based on developed models and tools; and raising public awareness in disaster readiness.
24 | Preparation and execution of work tasks regarding prevention and tackling with crisis situation | Implementing preventive measures in accordance with the law that regulates the competences of the Ministries and the other bodies of the national administration | CMC | The ministries and other bodies of state administration, public institutions and services and trade companies of special importance for work during crisis | Continuous activity | Continuous activity | According to the financial plans of the ministries and the other bodies of state administration, public institutions and services and trade companies, of special importance for work in crisis situations | Budget of the ministries and other bodies of state administration, public institutions and services and trade companies of special importance for work in crisis situations | Plans, programmes and reports for realized activities for implemented preventive and operational measures
25 | Preparation and execution of work tasks regarding prevention and tackling crisis situations on local level | Implementation of preventive measures in pursuance with the law that regulates the competences of the municipalities and the city of Skopje | CMC | Bodies of the municipalities and the city of Skopje, public institutions and services on local level | Continuous activity | Continuous activity | According to the financial plans of the municipalities | Budget of the municipalities and the city of Skopje | Plans, programmes and reports for realized activities for implemented preventive and operational measures
26 | Preparation of SUK for work in winter conditions | *clear thoroughfares * supply with fundamental groceries for the population and cattle | CMC on national and CMC on local level | Ministries, public enterprises, municipalities, city of Skopje and trade companies on contractual base | 1st and 4th quarter of each year | Continuous activity | According to the budgets of the subjects in SUK | budget of the subjects in SUK | * operational plans * reports for implemented activities (daily and periodical)
27 | Preparations of SUK for work in summer conditions | * extreme high temperatures and heat waves * fires on open space | CMC on national and CMC on local level | Ministries, public enterprises, municipalities, city of Skopje and trade companies on contractual base | May - September each year | Continuous activity | According to the budgets of the subjects in SUK | budget of the subjects in SUK | *preventive activities *early warning functions *operational plans * reports for implemented activities (daily and periodical)
28 | Operational and professional support in the General Staff and the governmental bodies (Group for assessment and Steering Committee) | Preparation of materials (information, tables, reviews, maps, minutes, information tools, etc.) for professional support | CMC | Ministers, directors of institutions and other representatives of the subjects of SUK | Dynamic plan of SAPDZDiVT of SUK | Dynamic plan of SAPDZDiVT of SUK | Regular budget of CMC | Budget of RNM | Number of information, tables, reviews, maps, minutes, information tools, etc.
29 | Organizing preparatory meetings with subjects on local level, keeping regional staffs and their registration | Preparation of materials (information, tables, reviews, maps, minutes, information tools, etc.) for professional support on local level | CMC | Bodies of the municipalities and the city of Skopje, public institutions and services on local level | Continuous activity | Continuous activity | Regular budget of CMC | Budget of RNM | Plans, programmes, reports and analyses for realized activities for implemented preventive and operational measures and risk assessment
30 | Organizing and coordinating the activities for tackling crisis situation declared on part of the territory of the Republic of North Macedonia due to increased scope of entry and transit of migrants/refugees throughout the territory of the Republic of North Macedonia | * functioning and coordinating of activities in PTC Vinojug and PTC Tabanovce *prevention of irregular migration | SOK, CMC Gevgelija and CMC Kumanovo | Representatives from the ministries and non-governmental humanitarian organizations (domestic and international) | Continuous activity | Until the crisis situation is over | budget of CMC | Budget of RNM | Number of information for the conditions in PTC Vinojug and Tabanovce * information for number of prevented irregular crossings and information of caught trafficking groups with migrants * number of weekly notifications towards the President, Government and the Assembly
31 | Organization and coordination of activities for tackling crisis situation, declared on the territory of the Republic of North Macedonia for protection of public health in conditions of pandemic declared by the World Health Organization from the infectious disease COVID-19 caused by the SARS-CoV-2 virus and for prevention of dissemination thus endangering the health safety of the people | Activities for securing covid centres and vaccination points | CMC | MoI, Army and MH (Covid centres and vaccination points) | Daily | Until the crisis situation is over | CMC Budget | Budget of RNM | Daily and weekly information
32 | Update and improvement of established data base on resources, monitoring daily events | *keeping resources base *keeping daily log base | CMC |  | Continuous activity | Continuous activity | CMC Budget | Budget of RNM | Number of data entered into the bases
33 | Leading urgent operational activities in CMC | *reception, selection and processing of received information *activities for engagement of resources of the entities of SUK on national and local level | CMC | All entities in SUK | Non-stop 24/7 | Non-stop 24/7 | CMC budget and budgets of entities of SUK and owners of resources | Budget of RNM | Number of daily and extraordinary information, reviews, bulletins and situation reports for events and occurrences.
34 | Protective equipment for forest fires |  | PENF | PENF | June |  | 2400000 | own funds
35 | Uniforms for forest guards |  | PENF | PENF | June |  | 6300000 | own funds
36 | Ammunition for forest guards |  | PENF | PENF | November |  | 700000 | own funds
37 | Stop batons |  | PENF | PENF | May |  | 60000 | own funds
38 | Tin tables |  | PENF | PENF | May |  | 240000 | own funds
39 | Back sprinklers for fire-fighting |  | PENF | PENF | February |  | 750000 | own funds
40 | Training for forest fire-fighters |  | PENF | PENF | February |  | 300000 | own funds
41 | Elaborate for geo-mechanics for the land (for training centre for fire-fighting in forests in Kavadarci) |  | PENF | PENF | January |  | 120000 | own funds
42 | Campaign for raising awareness among the citizens (media and lecture) |  | PENF | PENF | April |  | 1500000 | own funds
43 | Test certificates of the manufacturing works on vehicles |  | PENF | PENF | January |  | 200000 | own funds
44 | Upgrade of MKFFIS for preparation of protection reports |  | PENF | PENF | June |  | 1000000 | own funds
45 | Operational procedures for response of the healthcare sector in urgent, crisis situations and disasters | Response in time intervals of 24 hours, 48 hours, 72 hours, 7 days, 7-30 days and upon completion of the urgent, crisis situation and disaster | MH | General hospitals, clinical hospitals, specialist hospitals, university clinics, Red Cross, DPR, ARM, local self-government units, MoI, MLSP, Court medicine, PHI of the Republic of Macedonia, MAFWE, PHC | Continuous | Continuous |  | Budget of MH
46 | Standard operational procedure for public-health response in case of flood | Response in time intervals of 24 hours, 48 hours, 72 hours, 7 days, 7-30 days and upon completion of the urgent, crisis situation and disaster |  | General hospitals, clinic hospitals, specialist hospitals, university clinics, DPR, MoI, MoD, CMC, DPR, local self-government units, PHI of the Republic of Macedonia, PHC, DIZS, local self-government units | Continuous | Continuous |  | Budget of MH
47 | General operational procedures for communication in urgent, crisis situations and disasters | Response in time intervals of 24 hours, 48 hours, 72 hours, 7 days, 7-30 days and upon completion of the urgent, crisis situation and disaster | MH | General hospitals, clinic hospitals, specialist hospitals, university clinics, DPR, MoI, MoD, CMC, DPR, local self-government units, PHI of the Republic of Macedonia, PHC, DIZS, local self-government units | Continuous | Continuous |  | Budget of MH